## Sheet1
Requirements Traceability Matrix
Project Name: |  | Tasks.ogr |  | Document Author: |  | QA Team
Requirement ID | Requirement Name / Description | Requested / Approved By: | Scope Deliverable or Feature | Scope ID | User Story or Work Package | Assigned To | Test Case | Current Staus | Bug ID
Req - 1 | Add a New Task | Product Owner | Task Creation Workflow | Scope - 1 | As a user, I want to create a new task with a title and description so that I can keep track of my work | Hala Mousa | TC - 01 to TC - 14 | Failed | Bug - 1 / Bug - 2 / Bug - 3 / Bug - 4 / Bug - 5
Req - 2 | Edit an Existing Task | Product Owner | Task Editing Workflow | Scope - 2 | As a user, I want to edit an existing task so that I can update its details (e.g., title, due date) | Hala Mousa | TC - 15 to TC - 19 | Passed | ____
Req - 3 | Delete a Task | Product Owner | Task Deletion Workflow | Scope - 3 | As a user, I want to delete a task so that I can remove items I no longer need | Mohammad Badawi | TC - 20 to TC - 31 | Passed | ____
Req - 4 | Mark Task as Completed / Incomplete | Product Owner | Task Completion Workflow | Scope - 4 | As a user, I want to mark a task as completed or incomplete so that I can track my progress | Mohammad Badawi | TC - 32 to TC - 42 | Passed | ____
Req - 5 | Set Due Date & Time Reminder | Product Owner | Task Reminders & Notifications | Scope - 5 | As a user, I want to set a due date and reminder for a task so that I don’t forget deadlines | Saif Araj | TC - 43 to TC - 57 | Passed | ____
Req - 6 | Search Functionality | Product Owner | Task Search Workflow | Scope - 6 | As a user, I want to search for tasks so that I can quickly find the ones I need | Ahmed Abdallatif | TC - 58 to TC - 71 | Passed | ____
Req - 7 | Sort & Filter Tasks | Product Owner | Task Sorting & Filtering | Scope - 7 | As a user, I want to sort and filter tasks (e.g., by due date, priority) so that I can organize my list effectively | Ahmed Abdallatif | TC - 72 to TC - 86 | Passed | ____
Assigned To
Ahmed Abdallatif
Hala Mousa
Mohammad Badawi
Saif Araj
Current Staus
Passed
Failed